## Large Group SAG
Illinois Energy Efficiency Stakeholder Advisory Group (SAG)
Tracking Open Issues and Follow-up
January - December 2015 (meetings listed in reverse chronological order)
Document updated: 10/1/2015
Key:
*Open items are indicated in yellow highlight.
*SAG ACT refers to the SAG facilitation team.
*Large Group Monthly SAG meetings = SAG
*Subcommittee = Subcommittee Name
Note: This document only list topics with follow-up questions and/or action items. Click on the meeting link to view the agenda and additional meeting materials.
Large Group Monthly SAG Meeting: September 28-29, 2015 Meeting
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-09-28 | Open | SAG | Clean Power Plan - Overview of Final Rule (Julia Friedman, MEEA) | 1. Should SAG consider commenting on draft Clean Power Plan EM&V Guidelines as a group? Rob Neumann (Navigant) will present on this topic at the October SAG meetings. 2. SAG to discuss possible Clean Power Plan impacts at October SAG meetings. 3. SAG Facilitation will prepare a “Technical Position Paper” describing element of the CPP that should be considered or may influence the Portfolio Planning Process, for review and comment by the SAG. | October SAG meetings | To be discussed at October SAG.
2015-09-28 | Open | SAG | Illinois Energy Roadmap (Molly Lunn, Department; Kevin Green, Illinois EPA) | 1. The Department would like feedback on the data sets to use in the Roadmap efforts. The Roadmap will use the MARCI model. SAG will schedule a follow-up teleconference on modeling (SAG Facilitation will reach out to Mark Pruitt). The goal is to hold this teleconference in advance of the October SAG meetings 2. See above: SAG Facilitation will include in the “Technical Position Paper” any elements of the Illinois Energy Roadmap process that should be considered or may influence the portfolio planning process. | October SAG meetings | 1. Follow-up teleconference to be scheduled in October. 2. To be discussed at October SAG.
2015-09-28 | Open | SAG | Illinois NTG Working Group Update (Jeff Erickson, Navigant) | SAG participants will review the draft IL-NTG Methods document (to be circulated to SAG on Friday, October 2, 2015). SAG feedback is requested on: Basic methods; Protocols as drafted; Basic vs. standard/enhanced rigor; and Treatment of deferred free ridership. | 2015-10-15 | Draft methods document to be circulated to SAG for review/comment on Friday, October 2, 2015.
2015-09-28 | Open | SAG | Clean Power Plan Model (Becky Stanfield, NRDC) | SAG will schedule a follow-up teleconference tutorial on this model (meeting date TBD). | N/A | Meeting date TBD.
2015-09-28 | Open | SAG | SAG Portfolio Planning Process Kick-off (Annette Beitel, EE SAG Facilitator; Celia Johnson, SAG Facilitation) | Individual stakeholder outreach meetings will continue through October. If you would like to schedule an individual meeting to discuss this process and your organization’s high priority EE issues, please contact SAG Facilitation (Celia.Johnson@FutEE.biz). | N/A | Meetings will take place through October 2015.
2015-09-28 | Open | SAG | Proposed Path Forward – Planning Discussions (Kristol Whatley, Ameren IL) | Review the draft Consent Agreement/Proposed Stipulation and send comments/questions to SAG Facilitation (Celia.Johnson@FutEE.biz) within 10 business days (by COB on Thursday, 10/15/15). All comments/questions will be sent to Kristol Whatley, Ameren IL. | 2015-10-15 | See September 2015 Meeting Materials page to download the Draft Consent Agreement/Proposed Stipulation and Proposed Path Forward - Planning Discussions presentation.
2015-09-28 | Open | SAG | ComEd – Electric Program Year 7 Overview (Todd Thornburg, ComEd) | What is the penetration on the Residential Joint New Construction Program? Julie Hollensbe (ComEd) will look into this question. | N/A | Initial response provided in Attendee List/Action Items document. See Sept. 2015 Meeting Materials page.
2015-09-28 | Open | SAG | Ameren IL – Electric Program Year 7; Gas Program Year 4 Overview (Keith Goerss, Ameren IL) | 1. Energy Star New Homes Program – What is the penetration? Keith Goerss (Ameren IL) will look into this question. 2. Rural Efficiency Kits Program – How are kits received? Are low income customers eligible? Keith Martin (Ameren IL) will check on how kits are received. 3. Can gas measures be included in IPA programs to help deal with gas budget issues? SAG Facilitation will add this question to IPA policy discussion (currently scheduled in January 2016). | N/A | SAG Facilitation to follow-up.
2015-09-29 | Open | SAG | IL-TRM Overview (Cheryl Jenkins, VEIC; Sam Dent, VEIC) | 1. Persistence of savings for behavioral programs – The updated draft IL-NTG Methodologies includes this topic and will be circulated to SAG on Friday, Oct. 2nd for review and comment. Jim Jerozal (Nicor Gas) will input a placeholder on this topic on the IL-TRM tracker. 2. Oct. 1st workpaper deadline – Sam Dent (VEIC) will provide a list of the workpapers received by the deadline to TRM TAC (SAG Facilitation will circulate to SAG). This list will also indicate which items will be moved from “high” and “medium” priority items to “low” priority, or removed altogether, because material was not received on time. | N/A
2015-09-29 | Open | SAG | Department of Commerce and Economic Opportunity EPY7/GPY4 Portfolio Overview (Molly Lunn, Department) | 1. $6.9M of public sector was not used. How did the un-spent $ break down by Ameren IL and ComEd? Molly Lunn will follow-up. 2. Savings/participation/budget/TRC information is the completed template is still in draft. Molly Lunn will provide an updated overview template in a few weeks. The updated template will be circulated to SAG. | N/A | SAG Facilitation to follow-up.
2015-09-29 | Open | SAG | Nicor Gas Program Year 4 Overview (Jim Jerozal, Nicor Gas) | 1. Residential New Construction Program – What is the market share? Jim Jerozal (Nicor Gas) will follow-up. 2. What % of sales does 11.2M in therm savings represent? Ted Weaver (First Tracks Consulting/Nicor Gas) and Hammad Chaudhry (Nicor Gas) will follow-up. | N/A | SAG Facilitation to follow-up.
2015-09-29 | Open | SAG | Peoples Gas-North Shore Gas GPY4 Overview (Pat Michalkiewicz, Peoples Gas-North Shore Gas; Paige Knutsen, Franklin Energy, on behalf of PG-NSG) | 1. What is the total number of multi-family homes in Chicago? This program has served apx. 60,000 multi-family residences. Paige Knutsen will follow-up. 2. How much weatherization does PG-NSG incorporate? Measures were launched on Jan. 1, 2016. Paige Knutsen will follow-up on how things are going so far. | N/A | SAG Facilitation to follow-up.
2015-09-29 | Open | SAG | Overview of Issues – SAG Portfolio Planning Process (Annette Beitel, EE SAG Facilitator) | 1. SAG Facilitation will update the draft Project Plan and post to website/circulate to SAG. 2. Feedback on current Program Administrator Portfolios – Chris Neme (Energy Futures Group/NRDC) will present high level feedback on each EE Portfolio (slides) at the October SAG meetings. If you have Portfolio feedback to share that you would like to add to Chris Neme’s presentation, please coordinate with Chris directly (cneme@energyfuturesgroup.com). 3. Proposed New Program Idea Templates are due no later than Wednesday, November 4, 2015. If you need help filling out the Proposed New Program Idea Template or researching required information, please contact SAG Facilitation for assistance (Celia.Johnson@FutEE.biz). SAG participants are expected to make a good faith effort to fill out as much information as possible in this template by the due date. Additional information may be provided at a later time, if needed. | N/A
TRC Subcommittee Meeting #6: September 1, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
N/A | N/A | TRC Subcommittee | N/A | No follow-up items. | N/A | N/A | N/A | N/A
Large Group Monthly SAG Meeting: July 28, 2015 Meeting
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-07-28 | Open | SAG | Electronic TRM Presentations (Energy Resources Center, UIC; VEIC; Frontier Associates) | Question during VEIC Presentation: Is it possible for this to replace the paper IL-TRM? What would a hard-copy look like for those that are interested in downloading a PDF version? SAG ACT: Annette/Celia will follow-up with VEIC and send out an example to the group. Next steps on electronic TRM: SAG ACT: Annette/Celia to check with Program Administrator planners to see if there is interest in additional providers discussing electronic TRM options at a future SAG meeting. TBD. | 2015-09-15 | Electronic TRM options circulated to SAG on 8/19/15. | N/A
2015-07-28 | Open | SAG | Department of Commerce and Economic Opportunity Update (Molly Lunn, the Department) | IL Clean Energy Finance “Tune-Up” --SAG Participants: If you are interested in providing feedback into what goes into the initial recommendations (a memo), Molly is happy to do a call with key stakeholders. Contact Molly for more information. --SAG ACT: Annette/Celia to schedule a briefing on this topic at the October SAG meeting. | 2015-10-31 | To be scheduled for October 2015. | N/A
2015-07-28 | Closed | SAG | EE Successes Fact Sheet Reminder (Celia Johnson, SAG Senior Policy Analyst) | SAG Participants: Comments on the final draft Successes Fact Sheet are due by COB on Thursday, August 6th. A final version of the Successes Fact Sheet will be added to the SAG website by mid-August, with notice circulated to SAG. | 2015-08-06 | Updated Final Draft Fact Sheet documents circulated to SAG for review on 7/23/15. Comments due by COB on 8/6/15. Final Fact Sheet sent to SAG on 8/13/15. | See Successes Subcommittee page | 2015-08-13
2015-07-28 | Closed | SAG | Portfolio Planning Process (Annette Beitel, EE SAG Facilitator) | Sue Nathan, AEG: Draft a template that can be filled out across the Program Administrators (8-103, 8-104, and IPA). Completed templates will be discussed at the September meeting. Kristol Whatley, Ameren IL: Draft a proposed policy on settlement discussions. Draft a proposed stipulation. Roger Baker, ComEd: Organize the Program Administrators to review the draft schedule as a group, compared to internal utility timelines. Propose edits to SAG facilitation team by August 15th. SAG Participants: If any stakeholders or interested SAG participants have high level program suggestions for Program Administrators, please send by August 15 so that the utilities planning for upcoming Potential Studies may incorporate, as applicable. There will also be an opportunity for proposed ideas in the portfolio planning process, in the October/November timeframe. Question – is IPA law interpretation an item that can be discussed (there is pending litigation)? --SAG ACT: Annette/Celia to check on this. SAG ACT: Add process rules; update the project plan; add a timeline for new ideas/new measures, including changes to existing programs. To be discussed in September SAG. | Fall 2015 | Updated draft planning documents discussed at the September SAG meetings. Additional discussion will occur at the October SAG meetings. | N/A | 2015-09-30
TRC Subcommittee Meeting #6: July 21, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-07-21 | Open | TRC Subcommittee | Overall Impacts to TRC (Chris Neme, Energy Futures Group, on behalf of NRDC) | Chris Neme: Add discount rate and a section on low-income adders to the 'overall impacts to TRC' chart. SAG ACT: Celia will add the social discount rate versus cost-of-capital to Comparison Exhibit table. Updated chart will be posted to the TRC Subcommittee page prior to the final TRC Subcommitee meeting, with notice circulated. | 2015-09-15 | Final TRC Subcommittee meeting post-poned to later in 2015 (meeting date TBD). | N/A
2015-07-21 | Closed | TRC Subcommittee | Policy Impacts (Keith Goerss, Ameren IL | SAG ACT: Add a discussion item to the September 1st meeting – how can the IPA law be fixed? --Annette/Celia to follow-up with Keith Goerss on procedural ideas for circulation to the Subcommittee. --A summary table of policy impacts will be prepared and circulated prior to the Sept. 22nd meeting. TRC Subcommittee Participants: If you have additional policy impacts to add to the list described in the meeting notes, please send by COB on Friday, August 7th. | Additional policy impacts: 8/7/2015 | Discussed during TRC Subcommittee Meeting #7 (Sept. 1, 2015). | N/A
2015-07-21 | Closed | TRC Subcommittee | Non-Energy Benefits (Annette Beitel, EE SAG Facilitator) | Draft workpapers on existing measures are due August 1st to the TRM Administrator. Participants that plan to submit NEBs with a measure should consult with VEIC as to form, but should identify: measure, level of NEBs, source. | 2015-08-01 | NEBs to be addressed in IL-TRM Version 5.0 process. | N/A
2015-07-21 | Open | TRC Subcommittee | Additional TRC Issues (Jennifer Morris, ICC Staff) | Measuring Dual Baselines --SAG ACT: Where should the dual baselines policy be included in the future? Add this issue to Policy Manual Version 2. Measuring Interactive Effects --Phil Mosenthal: Review/propose edits to current IL-TRM language on interactive effects as alternate proposal. Subcommittee will discuss at 10/6 meeting. | Policy Manual v2: September, 2015 Interactive Effects: 9/15/2015 | To be discussed during TRC Subcommittee Meeting #8 (October 6, 2015). | N/A
2015-07-21 | Closed | TRC Subcommittee | TRC Reports (Celia Johnson, SAG Senior Policy Analyst) | SAG ACT: Move this discussion to Policy Manual version 2. There are a number of interrelated issues to other evaluation reports and proposed timelines. Addt'l discussion needed. | September, 2015 | Issue moved to Policy Manual version 2. | N/A
TRC Subcommittee Meeting #5: July 8, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-07-08 | Open | TRC Subcommittee | DRIPE Follow-up (Discussion of reports) (Annette Beitel, EE SAG Facilitator) | SAG ACT: Celia will update the draft DRIPE Comparison Exhibit to reflect comments during Meeting #5. In addition, prior to the final TRC Subcommittee meeting, an updated Comparison Exhibit will be prepared and circulated that identifies other non-consensus items that emerged in the TRC Subcommittee and that are not resolved prior to the final meeting. | 2015-09-15 | Final TRC Subcommittee meeting post-poned to later in 2015 (meeting date TBD). | N/A
Large Group Monthly SAG Meeting: June 23, 2015 Meeting
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-06-23 | Closed | SAG | IL-TRM Version 5.0 Measure List (Annette Beitel, EE SAG Facilitator) | Celia to update the tracker based on changes made in this meeting. Any additional items for the tracker must be added by COB on 6/24/15. | 2015-06-24 | Completed. Final priority tracker list circulated to SAG on 6/26/15. Final tracker list is available for download on the Meeting Materials page, TRM Administrator SharePoint site, and IL-TRM Version 5.0 page. | See IL TRM Version 5.0 page.
2015-06-23 | Open | SAG | Smart T-stat Collaborative and ComEd Home Energy Savings Program (John Paul Jewell, ELPC; Noel Corral, ComEd) | Navigant smart t-stat evaluation is in process. Add an agenda item to the October SAG meeting. Also add a presentation on Emerging Technologies Program t-stat results (Nicor Gas). | September, 2015 | To be scheduled for October 2015. | N/A
2015-06-23 | Closed | SAG | IL EE Successes Report-out (Jim Jerozal, Nicor Gas) | Successes Fact Sheet to be updated and circulated to SAG for review. | July, 2015 | Updated Final Draft Fact Sheet documents circulated to SAG for review on 7/23/15. Comments due by COB on 8/6/15. Final Fact Sheet sent to SAG on 8/13/15. | See Successes Subcommittee page | 2015-08-13
2015-06-23 | Closed | SAG | EE Jobs Multiplier (Karen Winter-Nelson, SEDAC; Ashley Harrington, 360 Energy Group; Ian Adams, Clean Energy Trust; Casey Bell, ACEEE) | EE jobs multiplier will not be included in Version 1. ACEEE will publish their suggested method for jobs in September 2015; follow-up on this discussion again in Version 2 of the Successes Fact Sheet (fall 2015). | Fall 2015 | To be discussed in Version 2 of the Successes Subcommittee - anticipated to begin in fall 2015. | N/A
TRC Subcommittee Meeting #4: June 16, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-06-16 | Open | TRC Subcommittee | TRC Subcommittee Report (Celia Johnson, EE SAG Facilitator) | Process next steps: 1) Jennifer Morris to discuss procedural options with OGC. (by 9/15/15) 2) Celia Johnson to update TRC Subcommittee Report to include executive summary; comparison exhibit; and consensus recommendations. 3) TRC Subcommitee Participants: Comments on policy implications due July 10th. | 2015-07-10 | No comments received on policy implications. Policy impacts and updated TRC Subcommittee Report to be discussed at the final TRC Subcommittee meeting (meeting date TBD). | N/A
2015-06-16 | Closed | TRC Subcommittee | Non-Energy Benefits (NEBs) (Celia Johnson, EE SAG Facilitator; Various) | Updates to NEBs Excel Document: Celia Johnson to research additional information in other jurisdictions break out Carbon, Water, NEBs and update the NEBs table as described in the meeting notes. In addition: *SAG Facilitation will e-mail Michael Li to see if UMP is going to address NEBs. *Chris Neme will ask Lisa Skumatz for more information. | N/A | SAG Facilitator update (7/21/15): NEBs will be addressed at the measure-level through IL-TRM Version 5.0 process. The NEBs research documents will no longer be updated. | N/A
2015-06-16 | Closed | TRC Subcommittee | DRIPE Update (Annette Beitel, EE SAG Facilitator) | SAG ACT: Post Exeter study, AESC study and IPA Report for review. Set up July 8 teleconference to discuss impacts of the studies on the prior analysis. Modify Comparison Exhibit to clarify it does not apply to gas or electric capacity. | 2015-07-08 | Teleconference held on 7/8/2015. Comparison Exhibit will be updated and discussed at the 9/22/15 meeting. | N/A
2015-06-16 | Closed | TRC Subcommittee | Overall Impacts to TRC Test | Chris Neme to develop a spreadsheet for July 21 meeting, including each utility and how much the adders increase net benefits. Will also add what would likely screen at measure/program level that does not screen now. | 2015-07-21 | Discussed during 7/21/2015 meeting. | N/A
Large Group Monthly SAG Meeting: May 11, 2015 Meeting
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-05-11 | Closed | SAG | PG-NSG Q3 Report-out; PY5 Update (Paige Knutsen, Franklin Energy on behalf of PG-NSG) | Home Energy Jumpstart video to be added to SAG meeting materials page. | N/A | Link added to May 11, 2015 Meeting Materials page. | See Meeting Materials | 2015-05-12
2015-05-11 | Closed | SAG | Successes Fact Sheet Report-out (Jim Jerozal, Nicor Gas) | 1) Jobs multiplier webinar - meeting (teleconference) invitation to be sent to SAG. 2) Successes Subcommittee to follow-up on suggestions; update Successes Fact Sheet. | N/A | 1) Jobs multiplier webinar held on 5/26/15 featuring Skip Laitner; SAG distribution list invited. 2) Successes Subcommittee follow-up call held on 5/20/15. Fact Sheet to be updated and discussed again at the June SAG meeting. | See Successes Subcommittee page | 2015-06-23
2015-05-11 | Open | SAG | Nicor Gas Wasted Energy Study (Chris Vaughn, Nicor Gas) | Are technical potential numbers available? Numbers are still being finalized. Nicor Gas will share when they are final. | N/A | Response to be added. | N/A
2015-05-11 | Closed | SAG | Natural Gas Self-Direct Program Evaluation Update (Stefano Galiasso, ERC/UIC) | The final self-direct report will be circulated to SAG. | N/A | Final report circulated to SAG on 6/24/15; it is also available for download on the meeting materials page. | See Meeting Materials | 2015-06-24
2015-05-11 | Closed | SAG | ComEd Q3 Report-out / Preview of PY8 (Ken Woolcutt, Ameren IL) | Schedule a follow-up presentation on smart t-stats. | June, 2015 | Follow-up discussion with ComEd and ELPC held during June SAG meeting. | Addt'l follow-up will be held in September 2015.
TRC Subcommittee Meeting #3: May 5, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-05-05 | Closed | TRC Subcommittee | Additional TRC Issues Raised by SAG - Interactive Effects and Dual Baselines (Jennifer Morris, ICC Staff) | Rob Neumann: 1) Dual Baselines: How difficult would it be to begin applying/using a dual baseline? Can Method 1 or any of the other methods be applied? 2) Interactive Effects: Can interactive effects be include for gas programs? Nicor Gas: Interactive Effects - 1) Is Nicor Gas willing to incorporate interactive effects in TRC? Dual Baselines - 1) How difficult would it be for Nicor Gas to incorporate dual baselines? Can the calculator be modified to take this into account? 2) Does the new version of E3 make it easier to incorporate dual baselines? SAG ACT: 1) Celia Johnson to update addt'l TRC issues response tracking document prior to next TRC Subcommittee meeting. | N/A | Interactive Effects and Dual Baselines follow-up was discused at the 7/21/2015 meeting. See action items above for 7/21. | N/A
2015-05-05 | Open | TRC Subcommittee | Additional TRC Issues Raised by SAG - Discount Rate (Phil Mosenthal, Optimal Energy, on behalf of IL AG) | Is Weighted Average Cost of Capitol (WACC) used before or after taxes? Hammad Chaudhry, Nicor Gas to check. Keith Goerss, Ameren IL to check. SAG ACT: 1) Celia Johnson to include a table of various approaches and rationale on using societal vs. WACC, in updated Comparison Exhibit. | 2015-09-15 | Updated Comparison Exhibit will be discussed at 9/22/2015 meeting. 1) Hammad C: It's pre-tax. | N/A
TRC Subcommittee Meeting #2: March 17, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-03-17 | Closed | TRC Subcommittee | Status of DRIPE Issue (Annette Beitel, EE SAG Facilitator) | Comments on draft DRIPE Comparison Exhibit and draft DRIPE Q&A document due by 4/1/2015. SAG Facilitator has requested additional responses to questions included in the Q&A document. SAG Facilitator to add qualifier language to both documents, explaining that the DRIPE discussion arose in an electric proceeding and further discussion on gas is needed. | 2015-04-01 | Participants determined that DRIPE Q&A document was not needed. DRIPE was discussed during 7/8/2015 teleconference. Updated Comparison Exhibit document will be discussed again at 9/22/2015 meeting. | N/A
2015-03-17 | Open | TRC Subcommittee | Should IPA run its own C/E calculations? (Anthony Star, IPA) | Chris Neme to follow-up on areas that need additional scrutiny, including whether IPA should complete scrunity independently. Consider developing table of all input assumptions, and what each utility is using (can indicate whether info is confidential, such as avoided costs). | N/A |  | N/A
2015-03-17 | Closed | TRC Subcommittee | Non-Energy Benefits (Lisa Skumatz, SERA; Chris Neme, Energy Futures Group, on behalf of NRDC) | Q: What is the multiplier in slide 12? (Lisa Skumatz) Q: What are actual studies supporting the values that NRDC recommends (Chris Neme) Q: What are NEBs in other jurisdictions? (Chris Neme) | N/A | NEBs research discussed during 6/16/2015 meeting. | N/A
2015-03-17 | Closed | TRC Subcommittee | Line Losses - Marginal vs. Average (Keith Goerss, Ameren IL) | Ameren IL will complete additional research and follow-up. | N/A | Line losses dicussed during 6/16/2015 meeting. | N/A
2015-03-17 | Closed | TRC Subcommittee | Additional TRC Issues (Jennifer Morris, ICC Staff) | TRC Subcommittee agreed to narrow the requests. Utilities and DCEO to follow-up on how interafctive effects and dual baselines are treated for IPA, 8-103 and 8-104 programs prior to the next Subcommittee call. | 2015-05-05 | Additional TRC issues discussed during 5/5/2015 teleconference and 7/21/2015 teleconference. | N/A
2015-03-17 | Open | TRC Subcommittee | Additional Action Items | 1) What is the overall impact of proposals? Are there additional analysis or questions that should be answered? 2) IPA to discuss SAG feedback on how they plan to address TRC calculation issues (DRIPE, NEBs, admin costs). | 2015-05-05 | 1) Overall impacts discussed during 7/21/2015 teleconference, and policy impacts was teed up during this meeting. Policy impacts to be discussed again during 9/22/2015 meeting. 2) IPA discussion will be held on 9/1/2015. | N/A
Large Group Monthly SAG Meeting: February 24, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-02-24 | Closed | SAG | Subcommittee Update - Annette Beitel, EE SAG Facilitator | EE Successes Subcommittee: if you would like to participate, email Celia by COB on 3/2 (celia.johnson@futee.biz). | 2015-03-02 | Successes Subcommittee (version 1) meetings completed. Version 2 to begin in fall 2015. | See Successes Subcommittee page
2015-02-24 | Closed | SAG | PG-NSG Programs Update and Q1-Q2 Report-out (Paige Knutsen, Franklin Energy, on behalf of PG-NSG) | Of the declined On-Bill Financing applications, what is the range of credit scores? Paige Knutsen to follow-up. | N/A | Follow-up response: This will likely be an issue addressed in an upcoming open docket. | N/A
2015-02-24 | Open | SAG | Ameren IL Q1-Q2 Report-out (Cheryl Miller, Jonathon Jackson, Ameren IL) | On-Bill Financing update: Cheryl Miller to confirm/follow-up on specific changes to OBF. 1) Can 100% of weatherization be covered? 2) Would it be possible to include windows in the Moderate Income Program with the changes to OBF? | N/A | Responses: 1) No, only those measures in Ameren Illinois' approved portfolio can be financed. There are exceptions to this for improvements associated with installation of approved measures which are not to exceed 25% of the project cost for necessary work. 2) No, only those measures in Ameren Illinois' approved portfolio can be financed. There are exceptions to this for improvements associated with installation of approved measures which are not to exceed 25% of the project cost for necessary work. | N/A | 2015-08-06
2015-02-24 | Open | SAG | ComEd Q1-Q2 Report-out (George Malek, ComEd) | George Malek to come back at a future SAG meeting to discuss monitoring-based commissioining, building analytics, and RCx. | N/A | To be scheduled in fall 2015. | N/A
2015-02-24 | Closed | SAG | Current DCEO Operations (Molly Lunn, DCEO) | If SAG participants have questions about proposed FY 2016 DCEO budget changes, contact Molly Lunn (marion.lunn@illinois.gov). 360 Energy Group is putting together a coalition to oppose EE funding "rollbacks." Contact Ashley Harrington (Ashley@360eg.com) if you are interested in joining or would like more information. | N/A | N/A | N/A
2015-02-24 | Open |  | IL Clean Jobs Legislation (Nick Magrisso, NRDC) | 1) Phil Mosenthal: Two recent studies indicate cost/unit energy of future savings will not be more expensive than cost/unit energy of past savings. 2) Schedule a follow-up presentation at a future SAG meeting on lighting opportunities (Phil Mosenthal). 3) Follow-up questions on legislation listed in the Meeting Notes document. A follow-up presentation will be scheduled in March to address questions. | Lighting Opportunities follow-up to be scheduled - fall 2015. | 1) Response to be added. 2) To be scheduled in fall 2015. 3) Follow-up presentation will not be scheduled at this time due to large group SAG meeting cancellation in March and April to complete Policy Manual v1. Legislation is still pending addt'l discussion by the IL legislature. | N/A
2015-02-24 | Open |  | Nicor Gas Emerging Technology Program (Chris Vaughn, Nicor Gas) | Nicor Gas and ComEd to co-present on smart t-stat findings at a future SAG meeting. | To be scheduled - September, 2015 | ComEd and ELPC presented on smart t-stats at the June SAG meeting. IL evaluator smart t-stat findings scheduled in Sept. 2015. Nicor Gas discussion on Emerging Tech Program t-stat results in Sept. 2015. | N/A
TRC Subcommittee Meeting #1: February 17, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-02-17 | Closed | TRC Subcommittee | DRIPE (Paul Chernick, Resource Insight, on behalf of NRDC; Scott Fisher, NorthBridge Group, on behalf of ComEd; David Brightwell, ICC Staff) | Updated draft DRIPE Comparison Exhibit and draft DRIPE Q&A document circulated for review on 3/10/2015. Comments on Comparison Exhibit due 3/16. Responses on open questions in draft Q&A Document due 3/25. | Comparison Exhibit: 3/15 Q&A: 3/25 | DRIPE was discussed during 7/8/2015 teleconference. Updated Comparison Exhibit document will be discussed again at 9/22/2015 meeting. | N/A
Large Group Monthly SAG Meeting: January 27, 2015
Date Assigned | Open / Closed | Meeting Type (SAG or Subcommittee) | Agenda Topic / Presenter(s) | Action Items | Due Date (if applicable) | Status and Notes (if applicable) | Additional Links (if applicable) | Date Completed
2015-01-27 | Open | SAG | Uniform Methods Project (Rob Neumann, Navigant) | Add TRM Regional Coordination to May large group SAG meeting. | May, 2015 | SAG F update: TRM Regional Coordination moved to fall 2015 | N/A
2015-01-27 | Closed | SAG | NTG Methodologies (Mary Sutter, Opinion Dynamics) | 1) Are protocols binding? Mary Sutter to provide draft language by COB 1/29. 2) If binding, is Staff giving up its right to approve? Jennifer Morris to discuss with OGC and follow-up by COB 1/30. 3) Can evaluators deviate with consensus of SAG? Mary Sutter to provide draft language by COB 1/29. 4) Does document apply equally to IPA, 8-103 and 8-104? Keith Goerss to check IPA law on evaluation and follow-up by 1/30. | 1) 1/29/2015 2) 1/30/2015 3) 1/29/2015 4) 1/30/2015 | Completed. NTG Methodologies included as "Attachment A" to IL-TRM Version 4.0. SAG F update: Additional NTG Methodologies discussions are ongoing (small group, hosted by evaluators). Report-out scheduled at Sept. SAG meeting. | N/A | January, 2015
2015-01-27 | Closed | SAG | CHP Subcommittee Update (Annette Beitel, EE SAG Facilitator) | 1) Nicor Gas is researching CHP NTG values in other jurisdictions. Will send to Celia by COB Friday, 1/30. 2) CHP vs. fuel-switching: Add to Policy Manual Subcommittee. Ted Weaver and Phil Mosenthal to work on this topic. 3) "Large user" language for TRM - participants to review IIEC and ICC Staff proposals. Comments/edits due by COB on 2/6. | 1) 1/30/2015 2) Spring 2015 3) 2/6/2015 | 1) Completed. CHP workpaper resolved. 2) Subcommittee determined it is not necessary to address fuel switching at this time. 3) Completed. CHP workpaper resolved. | See CHP Subcommittee (Subcommittee completed)
2015-01-27 | Closed | SAG | IL EE Successes Subcommittee (Annette Beitel, EE SAG Facilitator) | Email Celia by COB on 2/3 if you are interested in participating in this new Subcommittee (celia.johnson@futee.biz). Meeting invitations and materials will only be circulated to Subcommittee participants. | 2015-02-03 | Successes Subcommittee (version 1) meetings completed. Version 2 to begin in fall 2015. | See Successes Subcommittee page | 2015-02-03
2015-01-27 | Closed | SAG | DRIPE Discussion (Paul Chernick, Resource Insight on behalf of NRDC; Scott Fisher, NorthBridge, on behalf of ComEd) | TRC Subcommittee to be created (meeting 1: 2/17/15). Email Celia by COB on 2/3 to participate (celia.johnson@futee.biz). Meeting invitations and materials will only be circulated to Subcommittee participants. | 2015-02-03 | Meetings ongoing. | See TRC Subcommittee page | N/A - meetings ongoing